## Slide 1
Er. Jagmeet Kaur
E8387
ASSISTANT PROFESSOR
CSE
DISCOVER . LEARN . EMPOWER
University Institute of Engineering
DEPARTMENT OF COMPUTER SCIENCE & ENGINEERING
Subject Name: Software Engineering
Subject Code: 23CST-206
Software Design

## Slide 2
Software project planning
Project Estimation Techniques

## Slide 3: Software Project Planning
A Software Project is the complete methodology of programming advancement from requirement gathering to testing and support, completed by the execution procedures, in a specified period to achieve intended software product.
A project is well-defined task, which is a collection of several operations done in order to achieve a goal (for example, software development and delivery).

## Slide 4: Software Project Planning
A Project can be characterized as:
Every project may has a unique and distinct goal.
Project is not routine activity or day-to-day operations.
Project comes with a start time and end time.
Project ends when its goal is achieved hence it is a temporary phase in the lifetime of an organization.
Project needs adequate resources in terms of time, manpower, finance, material and knowledge-bank.

## Slide 5: Need of Software Project Management
Software development is a sort of all new streams in world business, and there's next to no involvement in structure programming items.
Most programming items are customized to accommodate customer's necessities.
The most significant is that the underlying technology changes and advances so generally and rapidly that experience of one element may not be connected to the other one.
All such business and ecological imperatives bring risk in software development; hence, it is fundamental to manage software projects efficiently.

## Slide 6: Software Project Manager
Software manager is responsible for planning and scheduling project development.
They manage the work to ensure that it is completed to the required standard.
They monitor the progress to check that the event is on time and within budget.
The project planning must incorporate the major issues like size & cost estimation scheduling, project monitoring, personnel selection evaluation & risk management.

## Slide 7: Software Project Manager
To plan a successful software project, we must understand:
Scope of work to be completed
Risk analysis
The resources mandatory
The project to be accomplished
Record of being followed

## Slide 8: Software Project Manager
A software project manager is a person who undertakes the responsibility of executing the software project.
Software project manager is thoroughly aware of all the phases of SDLC that the software would go through.
Project manager may never directly involve in producing the end product but he controls and manages the activities involved in production.

## Slide 9: Software Project Manager
A project manager closely monitors the development process, prepares and executes various plans, arranges necessary and adequate resources, maintains communication among all team members in order to address issues of cost, budget, resources, time, quality and customer satisfaction.

## Slide 10: Responsibility of Software Project Manager
Managing People :
Act as project leader
Liaison with stakeholders
Managing human resources
Setting up reporting hierarchy etc.

## Slide 11: Responsibility of Software Project Manager
Managing Project
Defining and setting up project scope
Managing project management activities
Monitoring progress and performance
Risk analysis at every phase
Take necessary step to avoid or come out of problems
Act as project spokesperson

## Slide 12: Software Management Activities
Software project management comprises of a number of activities, which contains planning of project, deciding scope of software product, estimation of cost in various terms, scheduling of tasks and events, and resource management. Project management activities may include:
Project Planning
Scope Management
Project Estimation

## Slide 13: Project Planning
Software project planning is task, which is performed before the production of software actually starts.
It is there for the software production but involves no concrete activity that has any direction connection with software production; rather it is a set of multiple processes, which facilitates software production.

## Slide 14
Software Project planning starts before technical work start. The various steps of planning activities are:

## Slide 15: Scope Management
It defines the scope of project; this includes all the activities, process need to be done in order to make a deliverable software product.
Scope management is essential because it creates boundaries of the project by clearly defining what would be done in the project and what would not be done.
This makes project to contain limited and quantifiable tasks, which can easily be documented and in turn avoids cost and time overrun.

## Slide 16: Scope Management
During Project Scope management, it is necessary to -
Define the scope
Decide its verification and control
Divide the project into various smaller parts for ease of management.
Verify the scope
Control the scope by incorporating changes to the scope

## Slide 17: Project Estimation
For an effective management accurate estimation of various measures is a must.
With correct estimation managers can manage and control the project more efficiently and effectively.
Project estimation may involve the following:
Software size estimation Software size may be estimated either in terms of KLOC (Kilo Line of Code) or by calculating number of function points in the software. Lines of code depend upon coding practices and Function points vary according to the user or software requirement.

## Slide 18: Project Estimation
Effort estimation : The managers estimate efforts in terms of personnel requirement and man-hour required to produce the software.
For effort estimation software size should be known.
This can either be derived by managers’ experience, organization’s historical data or software size can be converted into efforts by using some standard formulae.

## Slide 19: Project Estimation
Time estimation Once size and efforts are estimated, the time required to produce the software can be estimated.
Efforts required is segregated into sub categories as per the requirement specifications and interdependency of various components of software.
Software tasks are divided into smaller tasks, activities or events by Work Breakthrough Structure (WBS).
The tasks are scheduled on day-to-day basis or in calendar months.
The sum of time required to complete all tasks in hours or days is the total time invested to complete the project.

## Slide 20: Project Estimation
Cost estimation This might be considered as the most difficult of all because it depends on more elements than any of the previous ones. For estimating project cost, it is required to consider -
  Size of software
  Software quality
  Hardware
  Additional software or tools, licenses etc.
  Skilled personnel with task-specific skills
  Travel involved
  Communication
  Training and support

## Slide 21: Project Estimation Techniques
Project manager can estimate the listed factors using two broadly recognized techniques –
Decomposition Technique
This technique assumes the software as a product of various compositions.
There are two main models -
Line of Code Estimation is done on behalf of number of line of codes in the software product.
Function Points Estimation is done on behalf of number of function points in the software product.

## Slide 22: Project Estimation Techniques
Estimation is the process of finding an estimate, or approximation, which is a value that can be used for some purpose even if input data may be incomplete, uncertain, or unstable.
Estimation determines how much money, effort, resources, and time it will take to build a specific system or product. Estimation is based on −
Past Data/Past Experience
Available Documents/Knowledge
Assumptions
Identified Risks

## Slide 23: Project Estimation Techniques
The four basic steps in Software Project Estimation are −
Estimate the size of the development product.
Estimate the effort in person-months or person-hours.
Estimate the schedule in calendar months.
Estimate the project cost in agreed currency.

## Slide 24: Project Estimation Techniques
Empirical Estimation Technique
This technique uses empirically derived formulae to make estimation. These formulae are based on LOC or FPs.
Putnam Model This model is made by Lawrence H. Putnam, which is based on Norden’s frequency distribution (Rayleigh curve). Putnam model maps time and efforts required with software size.
COCOMO COCOMO stands for COnstructive COst MOdel, developed by Barry W. Boehm. It divides the software product into three categories of software: organic, semi-detached and embedded.

## Slide 25: Estimation Accuracy
Important factors that affect the accuracy of estimates are −
The accuracy of all the estimate’s input data.
The accuracy of any estimate calculation.
How closely the historical data or industry data used to calibrate the model matches the project you are estimating.
The predictability of your organization’s software development process.
The stability of both the product requirements and the environment that supports the software engineering effort.
Whether or not the actual project was carefully planned, monitored and controlled, and no major surprises occurred that caused unexpected delays.

## Slide 26: PROJECT ESTIMATION TECHNIQUES
Estimation of various project parameters is a basic project planning activity.
The important project parameters that are estimated include: project size, effort required to develop the software, project duration, and cost.
There are three broad categories of estimation techniques:
  • Empirical estimation techniques
  • Heuristic techniques
  • Analytical estimation techniques

## Slide 27: EMPIRICAL ESTIMATION TECHNIQUE
Empirical estimation techniques are based on making an educated guess of the project parameters.
While using this technique, prior experience with development of similar products is helpful.
Empirical estimation techniques are based on common sense, different activities involved in estimation have been formalized over the years.
Two popular empirical estimation techniques are: Expert judgment technique and Delphi cost estimation.

## Slide 28: Expert judgment technique Expert judgment technique
Experts divide a software product into component units:
  e.g. GUI, database module, data communication module, billing module, etc.
Add up the gauesses for each of the components.

## Slide 29: Delphi cost estimation
Delphi estimation is carried out by a team comprising of a group of experts and a coordinator.
In this approach, the coordinator provides each estimator with a copy of the software requirements specification (SRS) document and a form for recording his cost estimate.
Estimators complete their individual estimates anonymously and submit to the coordinator. In their estimates, the estimators mention any unusual characteristic of the product which has influenced his estimation.
The coordinator prepares and distributes the summary of the responses of all the estimators, and includes any unusual rationale noted by any of the estimators.
Based on this summary, the estimators re-estimate. This process is iterated for several rounds. No discussion among the estimators is allowed during the entire estimation process.
After the completion of several iterations of estimations, the coordinator takes the responsibility of compiling the results and preparing the final estimate.

## Slide 30: Heuristic techniques
Heuristic techniques assume that the relationships among the different project parameters can be modeled using suitable mathematical expressions. Once the basic (independent) parameters are known, the other (dependent) parameters can be easily determined by substituting the value of the basic parameters in the mathematical expression.
Different heuristic estimation models can be divided into the following two classes:
  Single variable estimation model: It provide a means to estimate the desired characteristics of a problem, using some previously estimated basic (independent) characteristic of the software product such as its size. A single variable estimation model takes the following form:
Estimated Parameter = c1 * ed1
  multivariable cost estimation model: takes the following form: Multivariable estimation models are expected to give more accurate estimates compared to the single variable models, since a project parameter is typically influenced by several independent parameters.
  Estimated Resource = c1*e1d1 + c2*e2d2 + ...

## Slide 31: References
https://www.tutorialspoint.com/software_engineering/software_project_management.htm
https://www.javatpoint.com/software-project-planning
https://www.tutorialspoint.com/estimation_techniques/estimation_techniques_overview.htm

## Slide 32
THANK YOU